AI Schema Builder

Project Plan & Product Roadmap

Version 1.0  |  2025

# 1. Project Summary

| Attribute | Detail |
| --- | --- |
| Project Name | AI Schema Builder |
| Project Owner | Engineering Lead |
| Start Date | Week 1 (Sprint 0) |
| Target MVP Release | Week 6 |
| Full Release (v1.0) | Week 12 |
| Team Size | 3–4 engineers |
| Tech Stack | React, Node.js, PostgreSQL, Google Gemini Claude API |

# 2. Sprint Plan

## Phase 1 — Foundation (Weeks 1–4)

| Sprint | Week | Feature | Owner | Story Points |
| --- | --- | --- | --- | --- |
| Sprint 1 | Wk 1–2 | Project setup, Auth (register/login/JWT) | Backend | 13 |
| Sprint 1 | Wk 1–2 | Database schema + migrations | Backend | 8 |
| Sprint 1 | Wk 1–2 | React app scaffold + routing | Frontend | 8 |
| Sprint 2 | Wk 3–4 | Project CRUD (create, list, update, delete) | Backend | 13 |
| Sprint 2 | Wk 3–4 | Table management (add, edit, delete tables) | Full Stack | 13 |
| Sprint 2 | Wk 3–4 | API Key management (encrypted storage) | Backend | 8 |
| Sprint 2 | Wk 3–4 | Project & Table UI components | Frontend | 13 |

## Phase 2 — AI Core (Weeks 5–8)

| Sprint | Week | Feature | Owner | Story Points |
| --- | --- | --- | --- | --- |
| Sprint 3 | Wk 5–6 | Gemini API integration + prompt engineering (Free) | Backend | 21 |
| Sprint 3 | Wk 5–6 | Schema generation endpoint | Backend | 13 |
| Sprint 3 | Wk 5–6 | Schema editor grid UI | Frontend | 13 |
| Sprint 3 | Wk 5–6 | Error handling + retry logic | Backend | 8 |
| Sprint 4 | Wk 7–8 | FK reference detection via Claude | Backend | 13 |
| Sprint 4 | Wk 7–8 | Reference accept/reject UI | Frontend | 8 |
| Sprint 4 | Wk 7–8 | Interactive ERD visualization (React Flow) | Frontend | 21 |
| Sprint 4 | Wk 7–8 | Schema versioning | Backend | 8 |

## Phase 3 — Polish & Launch (Weeks 9–12)

| Sprint | Week | Feature | Owner | Story Points |
| --- | --- | --- | --- | --- |
| Sprint 5 | Wk 9–10 | SQL DDL export (PostgreSQL/MySQL/SQLite) | Backend | 13 |
| Sprint 5 | Wk 9–10 | JSON schema export | Backend | 5 |
| Sprint 5 | Wk 9–10 | ERD PNG/SVG export | Frontend | 8 |
| Sprint 5 | Wk 9–10 | End-to-end testing | QA | 13 |
| Sprint 6 | Wk 11–12 | Team/multi-user project sharing | Full Stack | 21 |
| Sprint 6 | Wk 11–12 | Performance optimization + caching | Backend | 8 |
| Sprint 6 | Wk 11–12 | Production deployment (AWS) | DevOps | 13 |
| Sprint 6 | Wk 11–12 | Documentation & user guide | Team | 8 |

# 3. Team & Roles

| Role | Responsibilities | Count |
| --- | --- | --- |
| Backend Engineer | API design, Claude integration, DB schema, auth, exports | 1–2 |
| Frontend Engineer | React UI, ERD visualization, schema editor, export UX | 1 |
| DevOps / Infra | Docker, CI/CD, AWS deployment, monitoring | 0.5 (shared) |
| QA Engineer | E2E testing, performance testing, regression suite | 0.5 (shared) |
| Product Owner | Requirements, backlog grooming, stakeholder updates | 0.5 (shared) |

# 4. Risks & Mitigations

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Gemini API latency > 5s for complex schemas | Medium | High | Async generation with polling; show progress indicator |
| Gemini free tier rate limits hit (250 req/day, 10 RPM) | Low | Medium | Implement exponential backoff; test with lower volume |
| ERD becomes unreadable for 50+ tables | Medium | Medium | Auto-layout + filter/search for large projects |
| Schema JSON parse failures from Gemini | Low | High | Strict prompt + JSON validation + retry logic |
| Scope creep on team features | High | Medium | Lock Phase 3 scope before Sprint 5; defer extras to v1.1 |

# 5. Definition of Done

- All acceptance criteria for the story are met

- Unit tests written with > 80% coverage on new code

- Code reviewed and approved by at least one other engineer

- Deployed to staging and smoke-tested

- No open P0 or P1 bugs related to the story

- API documentation updated if new endpoints were added

# 6. Success Metrics

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Schema generation success rate | > 95% | API response logging |
| Average generation time | < 8 seconds | P95 latency monitoring |
| User task completion (schema to export) | < 5 minutes | Session analytics |
| Weekly active users (Month 1) | > 50 | User analytics |
| ERD accuracy (FK suggestions accepted) | > 70% | User acceptance rate in DB |

End of Project Plan